1999 World Hot Air Balloon Championship

Bad Waltersdorf, Austria

## Event Debriefing

# Briefing Rooms

- Need to improve sound system

- Turn speakers to stage so people up there can hear the questions from the audience

- No control of who came into rooms

- Mathijis felt that more crews should be allowed into the briefings (more per table)

- Noisy briefing area

- Rotate briefing table numbers to move people around the room

- Was task Briefing OK

  - Would have been nice to see visuals for weather (overhead projector)

  - Could improve task sheet, move more to top of form than bottom (Other programs available from Mathijis and Jack Bernadine are OK)

  - Better visual split of tasks on sheet

# Parking

- No fall back plan when launch field turned to mud

- Little room around the briefing center for parking

- Long way to walk from top of the launch field to briefing center

# Officials and Observers

- Staying in different hotels was good and bad

- Quality of observers was very good but some problems still encountered

- Observers marking center line – make sure they do it properly and once

- Some observers refused to go into maise even if only 3 meters, others went in a long ways

- Put inexperienced pilots and observers together

- Use free observers at scoring areas to help measuring team and watch for marker drops (Alex)

- No certification for debriefers, some debriefers correcting observer sheets when nothing was wrong with them

- Saga 97 was able to select best observers

# Communications

- Very difficult to get information from organizers and sometimes had very short time limits (eg. For deciding on rental vans)

- Organisers shifting timelines (web and mail information different) (e.g. event briefing time, prize giving date and time

- Observer invitation was a communications disaster, and very poorly done by Austria

  - Organisers had timetable from Les

  - Pilot invitation deadline was met by Austria

  - Officials and Observers invitations did not meet deadline

  - Problem was with Event Chief Observer

# ID cards

- Looks good but took a very long time to check in and do we really need a picture?

# Pre-Event

- Balloon shipping problems

  - Organizers required using one shipping agent

  - Pilots should be able to use own shipping agents

- *** CIA Needs paper on guildelines for shipping balloons around the world

- Van rental prices with Citroen were very good

- Pre event propane was too expensive at Gerhart Kindermans service station

- Suggest propane should be free or at reduced rates for pilots arriving days earlier, but would be expensive to organizers and propane sponsor.

- Pilots feel this event was expensive

  - All costs should be published well before the event

  - Felt event was making money off pilots

  - First pilot propane fill should be paid by organizers

  - Organizers wanted $1.5 million for insurance which cost pilots additional to buy

  - Were going to charge pilots to use ham radios in Austria

  - Need frequency assignments and radio guidelines well before the event

# Pilots

    - Discrepancy of pilot skills (Les Purfield)

    - Only best pilots should be at Worlds and others to WAG

    - Consider using USA format of cutting bottom 25 pilots after 3 days

    - Or put a flag on the crownline identifying inexperienced pilots

# Task Related

- Liked the idea of gravity drops

- Like the cancelled maximum double drop task

    - Pilots dissatisfied with maize issue and rules related to it

- Twirling marker modifies and makes it more streamlined when falling

- Get observer to write time differences between their watch and Director time on the task sheet (Uwe), but Masashi disagrees that it is needed

- Danny Galbraith (AUS) is color blind and sometimes did not see targets because of target colors

- Suggestion by Mathijis that CIA make and keep targets and give to organizers to use

- Standarize color jackets/shirts for officials, observers, etc at events

- Pilots would like to see results as soon as possible event if incomplete

- Initial results should have been displayed on result sheet  Program should have been fixed when requested by Jury.  Event Director should have made it happen.

- Jury found lots of problems on task sheets and checked all task sheets after that.

- Competition rules only requires that rule number broken be listed, but it would be helpful if a descriptive comment was added to each penalty.

- Discussion about how detailed Observer sheets should be

- Suggestion that Pilot signature can indicate that it is an estimated result (maybe a check box)

- Disccussion on rounded score results and accuracy of measurement (issue that John Grubstrom raised)

# Other Comments

- Australia – liked CIA Question and Answer meeting and event debriefing

- Important to have RECALL procedure at Worlds